## Summary
Initial post | Issue | Summary | Discussions on <ianaxfer@nro.net> | CRISP Team Status
2014/12/19 (Richard Hill) "Internet Number Community IANA Stewardship Proposal:First Draft" | Intellectual Property Rights | Discussion on how to address the IP rights of IANA trademark and iana.org domain name | Question raised from Seun Ojedeji on the need for agreement by IETF and names community on transfer to IETF Trust. | Completed. CRISP Team position shared on <ianaxfer@nro.net> list. (2015/01/02 UTC16:27 Andrei Robachevsky "IPR considerations in the RIRs submission to the ICG") CRISP Team to reflect Andrei's summary in the 2nd draft proposal . It is acknowleged by CRISP Team coordination with IETF and names community to tranfer to IETF Trust. At the same time, CRISP Team has considered it is important to describe and express what is requested from the perspective of the number resources communities.
2014/12/19 (Richard Hill) "Internet Number Community IANA Stewardship Proposal:First Draft" | Intellectual Property Rights | The generis data base rights that ICANN might have regarding the top-level allocations that it publishes. | It could be assumed the rights in this context will be as defined in global policies/agreement
2014/12/23 (Alan Barrett) "IANA IPR considerations" | Intellectual Property Rights | Discussion on how to address the IP rights of IANA trademark and iana.org domain name | Same as "2D"
2014/12/26 (Andrew Dul) "Internet Number Community IANA Stewardship" | Intellectual Property Rights | Clarification about the rights related to in-addr.arpa and ip6.arpa: It would seem at the moment that those domains are held by the IETF, and thus would be covered under the protocols response to the ICG? | No further discussions
2014/12/19 (Seun Ojedeji) "Internet Number Community IANA Stewardship Proposal:First Draft" | Proposal edits suggestions | Removing entire first paragraph in Section III and changing the word "contract" to "agreement" | Agreement that "contract" is the correct word. Ongoing over the need of the wording in the first paragraph of Section III Agreement that the wording in the first paragraph of Section III has been moved to Section II is an adequate place. | Completed. CRISP Team position shared on <ianaxfer@nro.net> list and agreed. (Izumi Okutani 2014/01/04 "Status on Comments received") No revision needed to the latest draft proposal.
2014/12/19 (Seun Ojedeji) "Internet Number Community IANA Stewardship Proposal:First Draft" | Contract | Should not be termed based indicated in section III but should have termination conditions. | Discussions on details of the contract continued. | Alan Barrett shared on <ianaxfer@nro.net> the CRISP Team discussions at the 8th call. Second draft in progress based on fixed term. A fixed term (with provision for periodic renewal) makes more sense for a few reasons: - renewal should not consume much additional resources over and above the periodic review which will be done in any case; - it makes it easier to revise the SLA from time to time; - it makes it possible to terminate the contract for reasons other than breach. - Not to give the message the current condition lasts indefinitely as default
2014/12/19 (Seun Ojedeji) "Internet Number Community IANA Stewardship Proposal:First Draft" | Review Committee | The Review committee may not be required. The review of compliance to agreement terms be handled mainly by the NRO-NC in conjunction with NRO-EC. | No further discussions | Completed. Discussed at the 8th call to select representatives in the same method and process as NRO NC from each RIR region. To be reflected in the second draft.
2014/12/19 (Seun Ojedeji) "Internet Number Community IANA Stewardship Proposal:First Draft" | Review Committee | The community of each RIR should elect a member while the chair of the NRO-EC at any point in time will be co-opted to serve as the review team (6 in total). | No further discussions
2014/12/23 (Seun Ojedeji) "IANA policy vis IANA operation - How they differ?" | Policy v Operations | Use existing structures, do not create new ones | Clarification was requested on the reason for not having NRO NC to conduct the review. | Completed. NRO NC provides advice to ICANN Board on Global policies. Review Committee is to provide input to NRO EC on operation of IANA function on number resources. It's roles and objectives are different, therefore have a separate selection process. The process of selecting Review Committee is proposed to be compatible with that of NRO NC.
2014/12/19 (Seun Ojedeji) "Internet Number Community IANA Stewardship Proposal:First Draft" | global PDP | Update of section 10 of the gPDP as follow: In case Step 9 (c), should at least *two* of the RIRs agree that changes need to be made | 1/3/2015 Seun Ojedeji asked for status regarding this item, Izumi Okutani replied explaining the CRISP team rationale for not including changes to the gPDP, that it should be changed under the regular process. Seun agreed that it did not have to be addressed as sufficient accountability is provided under the currren scheme. | Completed per agreement on the <anaxfer@nro.net> list this does not need to be addressed.
2014/12/23 (Seun Ojedeji) "Access to the recordings" | Recordings | Access to the recordings in user friendly format. Not able to access with Linux. | No further discussions | Completed. Updated from NRO secretariat to the <ianaxfer@nro.net> list, the recordings are made available on MP4 format for all past CRISP Team Meetings.
2014/12/20 (Seun Ojedeji) "Draft proposal differences" | Version Control | Version control on proposal | No further discussions | Agreed to incorporate. CRISP Team Member (Izumi Okutani) acknowledged the request on <anaxfer@nro.net> This is planned to be completed before publishing of the second draft.
2014/12/19 (MAEMURA Akinori) "JPNIC's comment for CRISP's initial draft" Item 1 (a and b) | Involvement by NTIA in operation of IANA function on number resources. | Check that the document makes it clear, especially for ICG members from other communities, that (a) there is no direct NTIA involvement, except (b) in conducting SLA reviews. | None. | Agreed to incorporate. Will be reviewed for the second draft.
2014/12/19 (MAEMURA Akinori) "JPNIC's comment for CRISP's initial draft" Item 2 a | Agreement (contract) with IANA function operator | Important to have SLA, ensure accountability, transparency of criteria and procedures, complaint resolution process. | None. | Completed. Details of SLA items are to be described in the seond draft.
2014/12/19 (MAEMURA Akinori) "JPNIC's comment for CRISP's initial draft" Item 2 b | Review committee qualifications | Review committee members should have sufficient knowledge. | None. | To be updated
2014/12/19 (MAEMURA Akinori) "JPNIC's comment for CRISP's initial draft" Item 2 b | Review committee process | It may be useful to define key points for the review. | None. | To be updated
2014/12/19 (MAEMURA Akinori) "JPNIC's comment for CRISP's initial draft" Item 2 b | Review committee appointment | Review committee members should be selected by RIR communities, similarly to NRO-NC/ASO-AC. They should not be appointed by NRO-EC. | None. | Completed. To be incorporated. See "Review Committee" column for details.
2014/12/30 (Andrew Sullivan) "Comments on CRISP proposal" | Wording of "delegation of the 'in-addr.arpa' and 'ip6.arpa' DNS trees" | "delegation of the 'in-addr.arpa' and 'ip6.arpa' DNS trees".Perhaps this means "delegation from". (IANA doesn't delegate those two names to any of the RIRs, but delegates spaces within them.) | Suggested text provided by Alan Barrett on <ianaxfer@nro.net> list and supported by Andrew Sullivan. | Completed. Text by Alan Barrett to be incorporated in the 2nd draft.
2014/12/30 (Andrew Sullivan) "Comments on CRISP proposal" | How to handle the case where number resources are the only function which needs change in the IANA operator. | the text does not seem to discuss the possibility of the NRO finding itself in the position of needing to change IANA operators, and yet being unable to get other IANA users to do the same thing. It might be worth saying something about how termination is expected to be handled. If this is implied in the retention of the existing framework, perhaps an additional sentence aking this slightly plainer would be helpful. | No further discussions | Completed. Discussed at the 8th call. To be incorporated in the second draft with other description on SLA.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Effect on the existing MoUs (NRO and ASO) | Confirmation about whether there is a need to change the existing MoUs | No further discussions | Completed. Raised on CRISP Team ML ("Need to change existing MoUs (NRO & ASO MoUs ) ?" Izumi Okutani) No objection to the interpretation that no changess are need to the existing MoUs, as neither MoUs cover operetion of the IANA function.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Review process on IANA function | Whether to include more details about the review process on IANA function for the number resources such as: - Frequency of review (every x year) - Disclosure of review report - Review committee selection and process conducted in an open and transparent manner - Principle for the RFP for a new contractor: to be conducted in a fair, open and transparent process in line with applicable industry best practices and standards (If the NRO EC determines that a change is needed with the IANA numbers function contract) | No further discussions | Completed. Discussed at the 8th call, making final confirmation within CRISP Team to incorporate the suggestion. In regards to frequency of the review, CRISP Team suggests to define maximum interval for the review and keep the flexibility to shorten the interval as needed.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | RIR Accountability | RIR accountability & oversight within their own regions is an important consideration. Every stakeholder should consider if the RIRs themselves are appropriately accountable to their members and stakeholders. | No further discussions | Completed. Discussed at the 8th call, observed the current description in Section II B is sufficient, with reference to RIR Governance Matrix. "The corporate governance documents and PDPs of each RIR and its community are accessible via the RIR Governance Matrix, published on the NRO website" No support observed over the need for additional accountability mechanism.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | RIR Accountability | Related point from above. Consider if a periodic review of the RIR's accountability to their members should be reviewed on a periodic basis and what form that formal review should take | No further discussions
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Determining support for the final proposal to ICG | How will the CRISP team determine support for the final draft from the global number resource community? - Will there a mechanism to proactively confirm support/lack of support? | No further discussions | Discussed at the 8th call . Agreed to follow the same process to collect feedback as the 1st and 2nd drafts. Feedback received can be confirmed by ICG via archives of <ianaxfer@nro.net> list
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Describe the global process in Section VI. | Missing details about the formation of the CRISP team: - the team's processes and methods for developing, publishing, receiving feedback from stakeholders - determining consensus on the final draft | No further discussions | Will work to incorporate in the 2nd draft.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Post the 2nd draft to the mailing list within an email in text format | Post the proposal in text format to facilitate discussions | No further discussions | Completed for the edited verision of the first draft and to be addressed also for the second draft.
2014/12/30 (Andrew Dul) "Internet Number Community IANA Stewardship Proposal: First Draft" | Real-time events to facilitate discussion | An open global conference call and/or global txt chat in a couple of different time zones to accommodate all members of the Internet community | No further discussions | Completed. Discussed at the 7th call and no consensus to organize such events: Questions raised by several CRISP Team members on how we position feedback and questions on the events. It was agreed all feedback and questions be sent in written form to <ianaxfer@nro.net> for CRISP members to address without misunderstanding. For time zone issue, the recordings are made available on the NRO webite and questions can be raised on the <ianaxfer@nro.net> list.
2015/1/4 (Filiz Yilmaz) "Internet Number Community IANA Stewardship Proposal: First Draft" | Some editorical suggestions made on 3 points. | 1. Add " providing secretariat roles." to describe RIR in PDP 2. Provide full name of "ICC" for arbitration 3. Add "together with their communities collectively." in description of Review Committee and RIR involvement | No further discussions | Completed. Incorporate the suggestions in 2nd draft.
N/A Raised within CRISP Team | Editorial changes to the first draft for more clarify | To describe response in the same as questions listed in each Section. No changes will be made to contents from the first draft. | N/A | Completed. Editorial version posted on CRISP Team webpage and announced on <ianaxfer@nro.net> list.
N/A Raised within CRISP Team | Work on improvement for "Section V NTIA Requirement" | Describe more clearly how our propose meets the requirements by NTIA | N/A | Completed. Draft text calling for final comments on CRISP Team ML.
N/A Raised within CRISP Team | Fill in all regional processes in Section VI, | Fill in information in ARIN and LACNIC regions | N/A | Currently worked on by volunteers from LACNIC and ARIN regions.
N/A Raised within CRISP Team | Fill in CRISP Team selection process of each region in Section VI, | Fill in information in AFRINIC and APNIC regions | N/A | Information for APNIC region completed. Information for ARINIC region update is work in progress..
N/A Rasied within CRISP Team | SLA - Main sections and relevant principles | First draft of SLA main sections and relevant prinicples v1.0 | N/A | Completed. Draft shared by Paul Rendek, called for comments from CRISP Team. Have been incorporated into the second draft.